## Status Report
Status Report for Team #5
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-04-01 | Overall Status: | Yellow
Contact: | Dominic | Explanation: | Just a little behind at the moment. Trying to figure out how to connect React to the Spring Boot project.
Prepared By: | Dominic
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Louis | Dao, Controller and Test class for Item entity & display of items in cart page
Raheleh | Purchase entity
Dominic | Dao, Controller and Test class for Customer entity, Test class for Purchase, Bug and error fixes
Justin | Address and Exchange Daos and Test classes, home page
Everyone | ERD, SQL DDL created
ID # | Key Issues | Action Plan |  |  | Status
None
1 | Being behind schedule | work more??? |  |  | in progress
2 | React and Spring Boot connection | read more on it |  |  | in progress
3 | Axios or fetch? | do some testing and take the better one |  |  | in progress
Critical Milestones |  | Health | Due Date | Comment/Status %
SQL Database |  | Green | 2021-04-01 | 100%
Daos Layer |  | Green | 2021-04-02 | 100%
Testing |  | Green | 2021-04-02 | 100%
Service Layer |  | Yellow | 2021-04-05 | 60%
Controllers Layer |  | Yellow | 2021-04-05 | 40%
React/Visual Interface |  | Yellow | 2021-04-07 | 20%
Validation |  | Red | 2021-04-07 | 0%
Presentation |  | Yellow | 2021-04-08 | 0%