## Status Report
Status Report for Team #5
Project |  | Status: (Red/Yellow/Green)
Date: | 2021-04-07 | Overall Status: | Green
Contact: | Justin | Explanation: | Found a way to connect React + Spring Boot + MySql a different way without the need for refactoring.
Prepared By: | Justin
Key Accomplishments
List key tasks and milestones achieved in this period, along with any key changes
Person Name | Task
Louis | Worked with the Service Layer. Added user inputs to shopping cart page and connect them to backend, Address and Exchange Daos and Test classes, home page
Raheleh | Can display Exchange Rate in shopping cart. Display Purchase History in another page. Connect React and mysql ,Purchase entity
Dominic | Continued on the Customer Page. Worked on the service layer,Dao, Controller and Test class for Customer entity, Test class for Purchase, Bug and error fixes
Justin | Adding to cart sends data. More CSS. Worked on frontend for store page and fixed the CSS,Address and Exchange Daos and Test classes, home page
Everyone | ERD, SQL DDL created
ID # | Key Issues | Action Plan |  |  | Status
1 | Need to refactor Dao, React pages, add repository | Assign Dao, Controllers, Repository and React pages to team members for refactoring |  |  | Done
2 | React and Spring Boot connection | read more on it |  |  | Done
3 | Axios or fetch? | do some testing and take the better one |  |  | Done
Critical Milestones |  | Health | Due Date | Comment/Status %
SQL Database |  | Green | 2021-04-01 | 100%
Daos Layer |  | Green | 2021-04-02 | 100%
Testing |  | Green | 2021-04-02 | 100%
Service Layer |  | Green | 2021-04-06 | 100%
Controllers Layer |  | Yellow | 2021-04-07 | 80%
React/Visual Interface |  | Yellow | 2021-04-07 | 80%
Validation |  | Red | 2021-04-08 | 0%
Presentation |  | Yellow | 2021-04-08 | 0%